## Progress
# | Module | Description | Current Issues | Status | Brahm Approval (Done / Not Done)
1 | Login | User will enter the url and try to login with given credentials | No Issue | Done | Done
2 | Logout | User can logout from the top right link any time (Only after login) | No Issue | Done | Done
3 | Change Password | After Login on the top right corner, user will see his / her username. On hover username, user can see change password link, clicking on the same will result into change password page. User need to enter Old, New and Confirm Password | After Change Password and Display of Confirmation Message - Pls Redirect to Home Screen (DONE) | Done | Done
4 | Forgot Password | User will click on forgot password form, it will go on forgot password link. In this form user will enter username and email. If both matches in the database, then email will go in the defined format with default change password. User can login with detail only one time and need to change his / her password after successfull login, if he / she will not do that temp password will expire and user needs to again use forgot password tool to get temporary password. | Don’t Have Email So cant Check (DONE) | Done | ?
5 | Configure Dashboard designs | Once Logged in Super admin can navigate these links | No Issues on Design | Done | Done
6 | MANAGE STATE | This form will be used for add / update / delete / download / list / search / Block State. It will be done by IIRPL Super Admin Only. | :- All is Ok , When Deleted - Do Not Remove the Deleted Entery From the Gride Below - Just that It Should Be Visible and No Action Possible on It . This is Universal Check (DONE) :- Check Server Date and Time Stamp - This is Universal Check :- On Delete - Pleae Ask For Entering Pasword in POP UP . | Done | Done _ Subject to Remarks being Implemented .
7 | MANAGE CITY | This form will be used for add / update / delete / download / list / search / Block City. It will be done by IIRPL Super Admin Only. | :- Deleted / Blocked States Should Not be Appearing Here and Should Not be Able for Selection . By Default For all Form Entry/Upload is Possible Only if the Status of a Particular System ID Item is Active. This Effects All Such Itesm and is a Universal Check (DONE) :- After Show All If You Sort the Show All Effect is Gone and It Returns to First Page. If after Show All Sorting is USed - The Effect of Show All to Stay . This Effects All Grids and is a Universal Check (DONE) | Done | Done _ Subject to Remarks being Implemented .
8 | MANAGE COMPANY | This form will be used for add / update / delete / download / list / search / Block Company. It will be done by IIRPL Super Admin Only. | All is OK , Except that Check of Manage State and Manage City on the Universal Check be Taken Care of . - Means All Universal Checks as explained here Be Taken Care Of . Another Example Being as if State Blocked or Deleted , we Cannot City , hence id Company is Blocked or Deleted we should not be able to selecte it Either (DONE) | Done | Done _ Subject to Remarks being Implemented .
9 | MANAGE BRANCH | This form will be used for add / update / delete / download / list / search / Block Branch. It will be done by IIRPL Super Admin Only. | All is OK , Except Means All Universal Checks as explained here Be Taken Care Of . :- Cannot Selecte Newly Created Company - Test New - Please Check :- Issue in all Selections (DONE. You can select only active companies. The "Test New" company is "deleted" thats why it is not appearing during company select.) | Done | Done _ Subject to Remarks being Implemented .
10 | OUTLET AREA | This form will be used for add / update / delete / download / list / search / Block Outlet Area. It will be done by IIRPL Super Admin Only. | All is OK , Except Means All Universal Checks as explained here Be Taken Care Of . On Edit - If No Values Changed _ It Saves Again - Please Check As Universal Check (DONE) | Done | Done _ Subject to Remarks being Implemented .
11 | OUTLET | This form will be used for add / update / delete / download / list / search / Block Outlet. It will be done by IIRPL Super Admin Only. | All Ok Except of Univeral Checks Beign Reconfirmed.. Issue Selecting New Company - Universal Check (DONE) | Done | Not Done
12 | Competition | This form will be used for add / update / delete / download / list / search / Block Competition Company. It will be done by IIRPL Super Admin Only. | Ok Subject to Active / Block / Delevte Status - Check Confirmed - Universal Check (DONE) | Done | Done _ Subject to Remarks being Implemented .
14 | Competition Brand | This form will be used for add / update / delete / download / list / search / Block Competition Brand. It will be done by IIRPL Super Admin Only. | Ok < Except Univeral Check Confrimation and New Company Selection Issues (DONE) | Done | Done _ Subject to Remarks being Implemented .
15 | MANAGE PRODUCT | This form will be used for add / update / delete / download / list / search / Block Product. It will be done by IIRPL Super Admin Only. | Ensure universal Checks - And Also when Seleting Multiple Branches - All Must be allotted Individaul System ID ( i.e Stored Individually Against Each Branches ) else it shall be an issue if we Save One ID Aginst Multiple Branchses - Means If We Have to Block In One Branch in This Mode We Cannot Do That - This is Univerrsal Check (DONE) | Done | Not Done
16 | MANAGE BRAND | This form will be used for add / update / delete / download / list / search / Block Brand. It will be done by IIRPL Super Admin Only. | Select Product Not Working - Hence Cannot Check On Error Message - All pre-Filled Data Is Getting Empty - Should Stay - this is Universal Check (DONE) | Done | Not Done
17 | MANAGE SKU | This form will be used for add / update / delete / download / list / search / Block SKU. It will be done by IIRPL Super Admin Only. | Select Product Not Working - Hence Cannot Check (It is working fine.their may be a probability that their is no prduct for company and branch u have selected.) On Error Message - All pre-Filled Data Is Getting Empty - Should Stay - this is Universal Check (in Progress) | Done | Not Done
18 | MANAGE COMPETITION SKU | This form will be used for add / update / delete / download / list / search / Block Copetition SKU. It will be done by IIRPL Super Admin Only. | Select Competitor's Product field is missing (Their is only 2 competitor management module i.e. a) Competitor brand b) Competitor company, to add Competitor's product we have to create a "Competitor's Product managment" module ) | Done
19 | ADD COMPANY BANNER |  |  | In Progress
20 | ADD PROMOS |  |  | In Progress
21 | ADD PROMO BANNER |  |  | In Progress
22 | ADD IIRPL USER |  |  | In Progress
23 | MAP IIRPL USER |  |  | In Progress
24 | Add Company User |  |  | In Progress
25 | Map Company User |  |  | In Progress
26 | Add Message |  |  | In Progress
27 | Add Tickler |  |  | In Progress
28 | Add New Sales |  |  | In Progress
29 | View Sales Report |  |  | In Progress
30 | Add New Photo |  |  | In Progress
31 | Add Multiple Photo |  |  | In Progress
32 | View Album |  |  | In Progress
33 | Download Sales Report |  |  | In Progress

## Credentials
http://netsetlabs.com/real_time_report admin / admin

## Checks
# | Check | Validation
1 | Mandotory | Could not be left emply
2 | Pin | 6 digit
3 | Phone | 11 digit, first digit will start from 0
4 | Select | Auto Increament drop down
5 | Enter | Text Box, enter a value
6

## Rules
Objective of the Project: The Objective of this project is to manage sales report within the given promo period, to assess the success / failure of the promo program run by innovativeincentives.in. There are 2 types of users: IIRPL (Staff) User and Company User. Further IIRPL users have 3 roles they could be Super Admin, Team Lead or Executive. Company User could have 4 roles: DSM, ASM, Manager and Admin. Following are the permissions of IIRPL User: 1) IIRPL Super Admin: All Section. He / She is the only user who can manage "Configure" section of the website. 2) Team Lead: Can't Access Configure, can do edit / delete and all other information (Generally will not do first level entry of sales) 3) Executive: Only do first level Entry only. Can't edit / download etc. No Access of Configure Section. Following are the permissions of Company User: 1) DSM: 2) ASM: 3) Manager: 4) Admin: General Instruction: * Difference between Block and Delete: Any record will never deleted from database. When any user will delete any record it will be non recoverable. If any record will be blocked, it could be recovered later. Block items are shown in red star icon and Unblock items are shown in green star icon in the grid of respecive section / module. Generic Checks: * Phone Number: 11 digit allow, first digit should be 0 * Pin: 6 digit only allowed. * Mandatory: Should have * red sign.